## Plan Details
Unique Id	Activity	Start Date	End Date	Percent completed	dependency	WBS
1	Setup	8-Jan-2013	31-Jan-2013	80		1.00
2	Finance spreadsheet and business case	8-Jan-2013	15-Jan-2013	90		1.10
3	Opt 1: Miss 1st May deadline (double check deadline)	8-Jan-2013	9-Jan-2013	0	2	1.11
4	Opt 2: Only raise £30k	8-Jan-2013	9-Jan-2013	0	2	1.12
5	Opt 3: Charge the school for electricity	8-Jan-2013	9-Jan-2013	0	2	1.13
6	PPA: research how hard is it?	8-Jan-2013	9-Jan-2013	0		1.14
7	Finace spreadsheet and business case to Nia	9-Jan-2013	9-Jan-2013	0		1.15
8	Register as an IPS	8-Jan-2013	21-Jan-2013	0		1.20
9	Model rule ammendments to cooperatives UK	8-Jan-2013	8-Jan-2013	0	7	1.21
10	Pay cooperatives UK	14-Jan-2013	14-Jan-2013	0	7	1.22
11	Set up bank account	22-Jan-2013	25-Jan-2013	0	7	1.30
12	Decide which bank - future loan potential	8-Jan-2013	22-Jan-2013	0	10	1.31
13	Decide which account	8-Jan-2013	22-Jan-2013	0	10	1.32
14	School and council negotiations and approval	8-Jan-2013	31-Jan-2013	0		2.00
15	Letters of support from councillors and MPs	8-Jan-2013	18-Jan-2013	40		2.10
16	Business case approved	9-Jan-2013	18-Jan-2013	40	6	2.20
17	Lease agreement signed	8-Jan-2013	31-Jan-2013	30		2.30
18	Get approval from Oncore to use their lease	8-Jan-2013	11-Jan-2013	0	16	2.31
19	GDPO and planning delays - check there are no issues	8-Jan-2013	31-Jan-2013	0		2.40
20	School negotiations	8-Jan-2013	31-Jan-2013	30		2.50
21	Letter of Intent	10-Jan-2013	1/18/2013	0		2.51
22	Briefing note	10-Jan-2013	1/15/2013	0		2.52
23	Meet with chair of governors and head teacher	1/21/2013	1/25/2013	0		2.53
24	Lease agreement signed	31-Jan-2013	31-Jan-2013	0	16	2.54
25	Marketing	14-Jan-2013	3/29/2013			3.00
26	Flyer, poster, website	14-Jan-2013	31-Jan-2013			3.10
27	Graphic design work	14-Jan-2013	31-Jan-2013		20	3.11
28	What can abundance do?	14-Jan-2013	11-Jan-2013		20	3.12
29	Social media campaign					3.20
30	Feb 8 Ed Davey event	8-Feb-2013	8-Feb-2013
31	Event at Fern Hill
32	Smarter Communities newsletter
33	Fern Hill newsletter
34	Councillors newsletters
35	Council newsletter
36	Prospectus				36,37
37	Write prospectus	1/8/2013	25-Jan-2013
38	Get prospectus approved that it doesn't break FSA rules	25-Jan-2013	2/8/2013
39	Meet with Derek Osbourne
40	Other local events?
41	Local businesses?
42	Flyers in local venues - health food shop, sports venues etc
43	Pledges
44	School governors
45	Personal networks
46	Fundraising - window of opportunity	2/8/2013	3/22/2013	0	24	4.00
47
48
49
50
51
52	PV spec and installation	1/8/2013	4/12/2013			5.00
53	Negotiate with suppliers					5.11
54	Timelines					5.12
55	Lump sum contract price					5.13
56	Health and safety and method of work					5.14
57	G59 agreements					5.15
58	Structural analysis					5.16
59	Finance and system size	3/22/2013	3/27/2013		45	5.20
60	Install	4/1/2013	4/12/2013		58	5.30
61	FiT account
62	Should IPS be VAT reged
63	School asbestos and other hazards report
	Find out if IPS pays corp tax
	Speak to RBK planning (eg Duty Planning Officer) to confirm scope of GPDOs, ie what we need to do to avoid planning permission entirely (incl max systen kWp)
	Speak to RBK building control to see if they need to be involved, or what we can do to avoid the need for them to be involved
	Get RBK to confirm no covenants or other procedural impediments from their side (eg needing permission of a committee that only meets twice per year!)